## Summary
DarkHorse - Delivery Plan (Azure, Continuum + ChickletFlow integration)
Plan start (Monday, Week 1) | 2026-10-26 | Edit this date and every date in the workbook shifts.
Duration | 26 weeks
Baseline | Extension v0.7.38; CPI-6 sprints 1-6 shipped
Architecture | docs/DarkHorse_09_Azure_Deployment.md
Releases
Release | Go-live (Fri) | Scope
R0 | 2026-11-20 | R0 - Azure Foundations (dev env live)
MVP | 2026-12-18 | MVP - DarkHorse on Azure, Continuum read integration, internal pilot
R2 | 2027-01-29 | R2 - Memory, Clean Core loop, full Continuum + ChickletFlow integration
R3 | 2027-03-12 | R3 - Marketplace, multi-model, private networking, dashboards
GA | 2027-04-09 | GA - Production hardening, client-tenant template, security sign-off
Sheets
Milestones | Key dates and exit criteria
Features | All features, release, status, weeks, effort, dependencies (edit start/end here)
Weekly Timeline | Gantt driven by Features start/end weeks
Release Plan | What goes live in each release and go/no-go
Integration | Changes needed in Continuum, ChickletFlow and DarkHorse
Azure Deployment | Azure rollout phases and environments
Effort by Workstream | Person-weeks per workstream and release
Risks & Questions | Risks and open decisions
Note | Integration changes are based on reading the Continuum (Next.js/Prisma) and ChickletFlow (FastAPI/Alembic) code in C:\99-AI Projects. Effort and week estimates are first-pass and owners are TBD.

## Milestones
# | Milestone | Week | Date (Fri) | Exit criteria
0 | M0 Kickoff | 1 | 2026-10-30 | Plan approved, owners assigned, Azure subscription and quota requests opened
1 | M1 Azure dev live (R0) | 4 | 2026-11-20 | IaC deployed, containers in ACR, CI/CD green, OpenAI + AI Search provisioned
2 | M2 Integration contract signed | 4 | 2026-11-20 | Event/ID contract agreed by DarkHorse, Continuum, ChickletFlow
3 | M3 MVP feature complete | 7 | 2026-12-11 | Editor -> APIM -> MCP/LLM proxy -> AI Search working with Entra auth and Continuum read
4 | M4 MVP go-live on Azure (internal pilot) | 8 | 2026-12-18 | Prod env up, one real RICEFW end to end, go/no-go passed
5 | M5 Hypercare exit | 10 | 2027-01-01 | Stable for 2 weeks, holiday period buffer, defects triaged
6 | M6 Continuum + ChickletFlow on Azure with SSO | 11 | 2027-01-08 | Both apps deployed, Entra SSO, auth on ChickletFlow
7 | M7 R2 release: integrated flow + memory | 14 | 2027-01-29 | Memory, Clean Core loop, push-back, webhook, StatusReporter live
8 | M8 R3 release: marketplace + private networking | 20 | 2027-03-12 | Agent marketplace, multi-model, dashboards, UAT complete
9 | M9 Security sign-off | 22 | 2027-03-26 | Pen-test findings closed, DR test passed
10 | M10 GA | 24 | 2027-04-09 | Production release, client-tenant template, support model live
Formulas:
Date (Fri) = Summary!$C4+7*([Week]-1)+4

## Features
ID | Workstream | Feature | Description | Release | Release week | Priority | Status | Start wk | End wk | Start date | End date | Person-weeks | Depends on | Owner | MVP?
A1 | Azure Platform | Azure landing zone + IaC | Bicep/Terraform: resource groups (dev/prod), Key Vault, ACR, Log Analytics, tagging, RBAC | R0 | 4 | High | Planned | 1 | 3 | 2026-10-26 | 2026-11-13 | 3 |  | TBD | Yes
A2 | Azure Platform | Azure OpenAI / Foundry deployments | Chat model + text-embedding-3 deployments; quota request; region and data-residency decision | R0 | 4 | High | Planned | 1 | 3 | 2026-10-26 | 2026-11-13 | 1 |  | TBD | Yes
A3 | Azure Platform | Azure AI Search + index schema v2 | Standard S1, semantic ranker, hybrid index with metadata fields (object type, C1 status, S/4 version, source) | R0 | 4 | High | Planned | 2 | 4 | 2026-11-02 | 2026-11-20 | 2 | A1 | TBD | Yes
A4 | Azure Platform | Containerize services | Dockerfiles for darkhorse-mcp, llm-proxy, ingest job (with headless Chromium), agent service; push to ACR | R0 | 4 | High | Planned | 3 | 4 | 2026-11-09 | 2026-11-20 | 2 | A1 | TBD | Yes
A5 | Azure Platform | Container Apps env + APIM + Front Door | Internal ingress behind APIM, custom domain, rate limits, audit logging | MVP | 8 | High | Planned | 4 | 6 | 2026-11-16 | 2026-12-04 | 3 | A4 | TBD | Yes
A6 | Azure Platform | Entra ID auth + managed identity | App registration, JWT validation in APIM, replace API keys (Search, OpenAI, Cosmos) with managed identity | MVP | 8 | High | Planned | 4 | 7 | 2026-11-16 | 2026-12-11 | 3 | A5 | TBD | Yes
A7 | Azure Platform | CI/CD pipelines | GitHub Actions: build, test, image scan, deploy dev/prod, scheduled ingest | R0 | 4 | High | Planned | 3 | 4 | 2026-11-09 | 2026-11-20 | 2 | A1 | TBD | Yes
A8 | Azure Platform | Observability + cost controls | App Insights, dashboards, alerts, budgets, token usage metering | MVP | 8 | Med | Planned | 6 | 8 | 2026-11-30 | 2026-12-18 | 2 | A5 | TBD | Yes
A9 | Azure Platform | Prod environment + go-live runbook | Prod resources, smoke tests, rollback plan, on-call, MVP cutover | MVP | 8 | High | Planned | 7 | 8 | 2026-12-07 | 2026-12-18 | 2 | A6,A8 | TBD | Yes
A10 | Azure Platform | Private networking | VNet integration, Private Endpoints for OpenAI/Search/Cosmos, no public access option | R3 | 20 | Med | Planned | 16 | 20 | 2027-02-08 | 2027-03-12 | 4 | A9 | TBD
A11 | Azure Platform | Per-client deployment template | Parameterized IaC for deployment into a client subscription/tenant + onboarding guide | GA | 24 | High | Planned | 20 | 23 | 2027-03-08 | 2027-04-02 | 4 | A10 | TBD
A12 | Azure Platform | DR, backup, load and pen-test remediation | Backups, RPO/RTO test, load test, fix security findings | GA | 24 | High | Planned | 21 | 24 | 2027-03-15 | 2027-04-09 | 3 | A9 | TBD
B0 | RAG & Knowledge | Ingest framework + 8 fetchers + Azure embedder/index | IFetcher/IChunker/IEmbedder/IVectorIndex; API Hub, Clean Core Guide, Arch Center, Help Portal | Shipped |  | High | Done |  |  |  |  | 0 |  | TBD
B1 | RAG & Knowledge | Scheduled ingest job on Azure | Container Apps Job (nightly/weekly), run history, failure alerts | MVP | 8 | High | Planned | 5 | 7 | 2026-11-23 | 2026-12-11 | 2 | A4,A3 | TBD | Yes
B2 | RAG & Knowledge | Re-ingest KB with hybrid + metadata filters | Re-embed existing sources into index v2; released-API / S/4 version / object type filters | MVP | 8 | High | Planned | 5 | 8 | 2026-11-23 | 2026-12-18 | 3 | A3,A2 | TBD | Yes
B3 | RAG & Knowledge | EDMX live run (XSUAA auth) | BTP trial / bearer token path to download EDMX from API Hub | R2 | 14 | High | Planned | 9 | 12 | 2026-12-21 | 2027-01-15 | 2 | B1 | TBD
B4 | RAG & Knowledge | help-portal-cds re-crawl | Re-crawl per-view detail pages to capture ABAP technical names | R2 | 14 | Med | Planned | 10 | 13 | 2026-12-28 | 2027-01-22 | 2 | B1 | TBD
B5 | RAG & Knowledge | KB coverage gap closure | Close gaps from DarkHorse_08_KB_Assessment.md (BAdIs, RAP, CBO patterns, released API lists) | R2 | 14 | High | Planned | 11 | 14 | 2027-01-04 | 2027-01-29 | 4 | B8 | TBD
B6 | RAG & Knowledge | LearningPortalFetcher | Lowest-priority additional source | R3 | 20 | Low | Planned | 17 | 19 | 2027-02-15 | 2027-03-05 | 1 | B1 | TBD
B7 | RAG & Knowledge | Blob raw cache + ingest versioning | Store raw fetched docs in Blob, version index builds, rollback to previous index | R2 | 14 | Med | Planned | 9 | 11 | 2026-12-21 | 2027-01-08 | 2 | B1 | TBD
B8 | RAG & Knowledge | Retrieval quality eval harness | Golden set of Clean Core questions; precision/recall, groundedness checks; run on every KB change | MVP | 8 | High | Planned | 6 | 8 | 2026-11-30 | 2026-12-18 | 2 | B2 | TBD | Yes
C1 | MCP Server | MCP tools (verify_badi/exit, clean core level, CDS, EML, RAP, CBO) | Local MCP server with 9+ tools and static + Azure KnowledgeProvider | Shipped |  | High | Done |  |  |  |  | 0 |  | TBD
C2 | MCP Server | MCP HTTP/SSE transport + auth middleware | Confirm/enable network transport; validate Entra token; per-request tenant context | MVP | 8 | High | Planned | 3 | 5 | 2026-11-09 | 2026-11-27 | 2 |  | TBD | Yes
C3 | MCP Server | MCP uses managed identity for Search | Remove AZURE_SEARCH_KEY; Search Index Data Reader role | MVP | 8 | High | Planned | 5 | 6 | 2026-11-23 | 2026-12-04 | 1 | C2,A6 | TBD | Yes
C4 | MCP Server | New MCP tools | get_released_api, check_atc_cleancore, search_memory, save_memory | R2 | 14 | High | Planned | 12 | 14 | 2027-01-11 | 2027-01-29 | 3 | E2 | TBD
C5 | MCP Server | MCP rate limits, audit logs, tenant filters | Usage audit and per-client index filtering | R2 | 14 | Med | Planned | 13 | 14 | 2027-01-18 | 2027-01-29 | 2 | C2 | TBD
D1 | Agents & Pipeline | Grounded Code/TDS/SO/FDS agents | Agents call MCP for grounding before generation (CPI-6 sprints 3-5) | Shipped |  | High | Done |  |  |  |  | 0 |  | TBD
D2 | Agents & Pipeline | ReviewAgent + auto-rewrite + ZI_ wrappers | Independent LLM critic, direct-table SELECT rewrite, auto CDS wrappers (sprint 6) | Shipped |  | High | Done |  |  |  |  | 0 |  | TBD
D3 | Agents & Pipeline | TdsPostCodeAgent | Fills TDS program logic, CDS defs, test cases after code gen | Shipped |  | Med | Done |  |  |  |  | 0 |  | TBD
D4 | Agents & Pipeline | Solution architecture diagram | Mermaid call/dependency graph after code generation | Shipped |  | Med | Done |  |  |  |  | 0 |  | TBD
D5 | Agents & Pipeline | Headless agent service on Azure | Extract pipeline orchestration from the extension into a service API so Continuum/ChickletFlow can trigger runs | R2 | 14 | High | Planned | 9 | 14 | 2026-12-21 | 2027-01-29 | 6 | D6,C2 | TBD
D6 | Agents & Pipeline | LLM proxy on Azure | Azure OpenAI backend via adapter, PII/secret scrubbing, token metering, retries | MVP | 8 | High | Planned | 4 | 7 | 2026-11-16 | 2026-12-11 | 3 | A2,A5 | TBD | Yes
D7 | Agents & Pipeline | Clean Core validation loop | Generate, validate vs released APIs / ATC Clean Core, auto-retry, log violations for KB gaps | R2 | 14 | High | Planned | 9 | 13 | 2026-12-21 | 2027-01-22 | 4 | B2,C2 | TBD
D8 | Agents & Pipeline | Source citations in generated output | Attach retrieved chunk references to generated TDS/code | R2 | 14 | Med | Planned | 12 | 14 | 2027-01-11 | 2027-01-29 | 2 | D7 | TBD
D9 | Agents & Pipeline | Agent marketplace (Sprint 7) | Catalog, install and versioning of agents per docs/DarkHorse_06 Sprint 7 | R3 | 20 | Med | Planned | 15 | 20 | 2027-02-01 | 2027-03-12 | 6 | D5 | TBD
D10 | Agents & Pipeline | Multi-model routing | Azure OpenAI / Claude on Foundry / Ollama via adapter; per-agent model choice | R3 | 20 | Med | Planned | 14 | 17 | 2027-01-25 | 2027-02-19 | 3 | D6 | TBD
D11 | Agents & Pipeline | Prompt registry + eval regression suite | Versioned prompts, automated regression on golden FDS/TDS set | R3 | 20 | Med | Planned | 16 | 19 | 2027-02-08 | 2027-03-05 | 3 | B8 | TBD
E1 | Memory | Cosmos DB + memory schema | Provision Cosmos; session/project/user memory containers; partition by client/project | R2 | 14 | High | Planned | 8 | 10 | 2026-12-14 | 2027-01-01 | 2 | A6 | TBD
E2 | Memory | Session & project memory API | Memory read/write service + MCP tools; agents recall prior decisions | R2 | 14 | High | Planned | 10 | 13 | 2026-12-28 | 2027-01-22 | 3 | E1 | TBD
E3 | Memory | Correction Store indexed to AI Search | Developer edits (corrections/*.json) become retrievable long-term memory | R2 | 14 | High | Planned | 11 | 14 | 2027-01-04 | 2027-01-29 | 3 | E1,B2 | TBD
E4 | Memory | Approved-pattern library | Promote reviewed code to curated patterns; retrieval boost | R3 | 20 | Med | Planned | 15 | 18 | 2027-02-01 | 2027-02-26 | 3 | E3 | TBD
E5 | Memory | Memory governance | Retention, per-client isolation, PII purge, export | R3 | 20 | Med | Planned | 17 | 19 | 2027-02-15 | 2027-03-05 | 2 | E2 | TBD
F1 | Editor | Editor endpoint config + Entra sign-in | Settings for APIM URL per client; sign-in flow; token refresh | MVP | 8 | High | Planned | 5 | 8 | 2026-11-23 | 2026-12-18 | 3 | A6 | TBD | Yes
F2 | Editor | Extension v0.7.38 + version in status bar | Current editor extension baseline | Shipped |  | Low | Done |  |  |  |  | 0 |  | TBD
F3 | Editor | Pipeline UX for Azure status/errors | Clear surfacing of grounding failures, auth expiry, throttling | MVP | 8 | Med | Planned | 7 | 8 | 2026-12-07 | 2026-12-18 | 1 | F1 | TBD | Yes
F4 | Editor | Installer + update channel | Signed .vsix / fork builds, release channels (pilot/stable) | R2 | 14 | Med | Planned | 11 | 14 | 2027-01-04 | 2027-01-29 | 2 | F1 | TBD
F5 | Editor | Telemetry (opt-in) + usage dashboard | Adoption, generation success, Clean Core pass rate | R3 | 20 | Low | Planned | 16 | 18 | 2027-02-08 | 2027-02-26 | 2 | A8 | TBD
G1 | Continuum Integration | Continuum service-token API + OpenAPI spec | Machine auth for /api/w/[slug]/ricefws* (today session-only); documented contract | MVP | 8 | High | Planned | 3 | 6 | 2026-11-09 | 2026-12-04 | 3 | I2 | TBD | Yes
G2 | Continuum Integration | DarkHorse ContinuumClient (pull specs) | Fetch approved FDS/TDS sections by objectId as pipeline input | MVP | 8 | High | Planned | 5 | 8 | 2026-11-23 | 2026-12-18 | 3 | G1 | TBD | Yes
G3 | Continuum Integration | Push-back from DarkHorse | Create draft version / attachments: generated TDS, code, diagram, Clean Core report | R2 | 14 | High | Planned | 9 | 12 | 2026-12-21 | 2027-01-15 | 3 | G5,G2 | TBD
G4 | Continuum Integration | Approval webhook -> DarkHorse run | On APPROVED/PUBLISHED version, trigger agent service run | R2 | 14 | High | Planned | 11 | 14 | 2027-01-04 | 2027-01-29 | 3 | D5,G5 | TBD
G5 | Continuum Integration | Continuum schema additions | darkhorseRunId, cleanCoreScore, generated objects; TraceSystem DARKHORSE; Prisma migration | R2 | 14 | High | Planned | 9 | 11 | 2026-12-21 | 2027-01-08 | 2 | G1 | TBD
G6 | Continuum Integration | Continuum on Azure + Entra SSO | Container Apps + Azure Postgres Flexible; replace credentials auth with Entra | R2 | 14 | High | Planned | 7 | 11 | 2026-12-07 | 2027-01-08 | 4 | A1,I1 | TBD
G7 | Continuum Integration | Continuum AI via LLM proxy | Replace direct ANTHROPIC_API_KEY in lib/ai with Azure LLM proxy | R2 | 14 | Med | Planned | 10 | 12 | 2026-12-28 | 2027-01-15 | 2 | D6,G6 | TBD
G8 | Continuum Integration | Continuum UI: Generate with DarkHorse | Button, run status panel, Clean Core badge on RICEFW page | R3 | 20 | Med | Planned | 14 | 18 | 2027-01-25 | 2027-02-26 | 4 | G4 | TBD
H1 | ChickletFlow Integration | ChickletFlow auth (Entra + service tokens) | No auth today (CORS only); secure API and WebSocket | R2 | 14 | High | Planned | 6 | 9 | 2026-11-30 | 2026-12-25 | 3 | I1 | TBD
H2 | ChickletFlow Integration | Work item link fields | continuum_object_id, continuum_url, darkhorse_run_id, clean_core_score; Alembic migration | R2 | 14 | High | Planned | 8 | 10 | 2026-12-14 | 2027-01-01 | 2 | I2 | TBD
H3 | ChickletFlow Integration | Events endpoint + status_history source | POST /api/work-items/{id}/events; record source (user/darkhorse/continuum); broadcast over /ws/board | R2 | 14 | High | Planned | 9 | 12 | 2026-12-21 | 2027-01-15 | 3 | H2,H1 | TBD
H4 | ChickletFlow Integration | DarkHorse StatusReporter | Pipeline moves chicklets as run progresses (Build In-Progress, TS Updates/Code Review, blocked on failure) | R2 | 14 | High | Planned | 11 | 14 | 2027-01-04 | 2027-01-29 | 3 | H3,D5 | TBD
H5 | ChickletFlow Integration | Auto-status mapping rules | Continuum approval states and DarkHorse results map to board columns; configurable | R2 | 14 | Med | Planned | 12 | 14 | 2027-01-11 | 2027-01-29 | 2 | H3 | TBD
H6 | ChickletFlow Integration | ChickletFlow on Azure | Container Apps + Postgres Flexible; WebSocket ingress or Web PubSub; Alembic on deploy | R2 | 14 | High | Planned | 8 | 11 | 2026-12-14 | 2027-01-08 | 3 | A1 | TBD
H7 | ChickletFlow Integration | Board: run badge + delivery dashboard | DarkHorse run badge, Clean Core score, cycle-time / throughput by status | R3 | 20 | Med | Planned | 15 | 19 | 2027-02-01 | 2027-03-05 | 4 | H4 | TBD
I1 | Cross-Product | Unified identity (Entra groups/roles) | Common roles across DarkHorse, Continuum, ChickletFlow; group-based access | MVP | 8 | High | Planned | 5 | 8 | 2026-11-23 | 2026-12-18 | 2 | A6 | TBD | Yes
I2 | Cross-Product | Event and ID contract | Shared schema: RICEFW ID mapping, run events, statuses; versioned; sign-off by all 3 teams | R0 | 4 | High | Planned | 2 | 4 | 2026-11-02 | 2026-11-20 | 2 |  | TBD | Yes
I3 | Cross-Product | End-to-end UAT | Continuum approval -> DarkHorse -> code -> ChickletFlow status, across 5+ RICEFW types | R3 | 20 | High | Planned | 18 | 20 | 2027-02-22 | 2027-03-12 | 3 | G4,H4 | TBD
I4 | Cross-Product | Internal pilot on one RICEFW | End-to-end with a real object from Continuum Docs (e.g. RTR-R-0717 report) on Azure | MVP | 8 | High | Planned | 7 | 8 | 2026-12-07 | 2026-12-18 | 1 | G2,A9 | TBD | Yes
I5 | Cross-Product | Wider program pilot | Run on a full RICEFW backlog for one program; collect accuracy and time-saved metrics | GA | 24 | High | Planned | 21 | 23 | 2027-03-15 | 2027-04-02 | 3 | I3 | TBD
J1 | Release & Governance | Threat model + security design review | Data flows, secrets, tenant isolation; Azure Policy baseline | R0 | 4 | High | Planned | 2 | 3 | 2026-11-02 | 2026-11-13 | 1 | A1 | TBD | Yes
J2 | Release & Governance | Documentation + training | Admin guide, developer guide, runbooks, short training videos | GA | 24 | Med | Planned | 18 | 23 | 2027-02-22 | 2027-04-02 | 3 |  | TBD
J3 | Release & Governance | GA readiness + go-live | Go/no-go, support model, SLA, comms | GA | 24 | High | Planned | 23 | 24 | 2027-03-29 | 2027-04-09 | 2 | J4,I5 | TBD
J4 | Release & Governance | Security review + penetration test | External/internal pen-test of the 3 apps and Azure estate | GA | 24 | High | Planned | 21 | 23 | 2027-03-15 | 2027-04-02 | 3 | A12 | TBD
Formulas:
Start date = Summary!$C4+7*([Start wk]-1)
End date = Summary!$C4+7*([End wk]-1)+4

## Weekly Timeline
Weekly timeline (driven by Features start/end week; change them in Features)
| Week starting (Mon) |  |  |  | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19
ID | Feature | Release | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Milestones (diamond) | bar: 2026-10-26; 2026-11-16; 2026-12-07 to 2026-12-14; 2026-12-28 to 2027-01-04; 2027-01-25; 2027-03-08; 2027-03-22; 2027-04-05
| Releases (R0/MVP/R2/R3/GA) |  |  |  | 2026-11-16: R0; 2026-12-14: MVP; 2027-01-25: R2; 2027-03-08: R3; 2027-04-05: GA
Azure Platform
A1 | Azure landing zone + IaC | R0 | 1 | 3 | bar: 2026-10-26 to 2026-11-09
A2 | Azure OpenAI / Foundry deployments | R0 | 1 | 3 | bar: 2026-10-26 to 2026-11-09
A3 | Azure AI Search + index schema v2 | R0 | 2 | 4 | bar: 2026-11-02 to 2026-11-16
A4 | Containerize services | R0 | 3 | 4 | bar: 2026-11-09 to 2026-11-16
A5 | Container Apps env + APIM + Front Door | MVP | 4 | 6 | bar: 2026-11-16 to 2026-11-30
A6 | Entra ID auth + managed identity | MVP | 4 | 7 | bar: 2026-11-16 to 2026-12-07
A7 | CI/CD pipelines | R0 | 3 | 4 | bar: 2026-11-09 to 2026-11-16
A8 | Observability + cost controls | MVP | 6 | 8 | bar: 2026-11-30 to 2026-12-14
A9 | Prod environment + go-live runbook | MVP | 7 | 8 | bar: 2026-12-07 to 2026-12-14
A10 | Private networking | R3 | 16 | 20 | bar: 2027-02-08 to 2027-03-08
A11 | Per-client deployment template | GA | 20 | 23 | bar: 2027-03-08 to 2027-03-29
A12 | DR, backup, load and pen-test remediation | GA | 21 | 24 | bar: 2027-03-15 to 2027-04-05
RAG & Knowledge
B1 | Scheduled ingest job on Azure | MVP | 5 | 7 | bar: 2026-11-23 to 2026-12-07
B2 | Re-ingest KB with hybrid + metadata filters | MVP | 5 | 8 | bar: 2026-11-23 to 2026-12-14
B3 | EDMX live run (XSUAA auth) | R2 | 9 | 12 | bar: 2026-12-21 to 2027-01-11
B4 | help-portal-cds re-crawl | R2 | 10 | 13 | bar: 2026-12-28 to 2027-01-18
B5 | KB coverage gap closure | R2 | 11 | 14 | bar: 2027-01-04 to 2027-01-25
B6 | LearningPortalFetcher | R3 | 17 | 19 | bar: 2027-02-15 to 2027-03-01
B7 | Blob raw cache + ingest versioning | R2 | 9 | 11 | bar: 2026-12-21 to 2027-01-04
B8 | Retrieval quality eval harness | MVP | 6 | 8 | bar: 2026-11-30 to 2026-12-14
MCP Server
C2 | MCP HTTP/SSE transport + auth middleware | MVP | 3 | 5 | bar: 2026-11-09 to 2026-11-23
C3 | MCP uses managed identity for Search | MVP | 5 | 6 | bar: 2026-11-23 to 2026-11-30
C4 | New MCP tools | R2 | 12 | 14 | bar: 2027-01-11 to 2027-01-25
C5 | MCP rate limits, audit logs, tenant filters | R2 | 13 | 14 | bar: 2027-01-18 to 2027-01-25
Agents & Pipeline
D5 | Headless agent service on Azure | R2 | 9 | 14 | bar: 2026-12-21 to 2027-01-25
D6 | LLM proxy on Azure | MVP | 4 | 7 | bar: 2026-11-16 to 2026-12-07
D7 | Clean Core validation loop | R2 | 9 | 13 | bar: 2026-12-21 to 2027-01-18
D8 | Source citations in generated output | R2 | 12 | 14 | bar: 2027-01-11 to 2027-01-25
D9 | Agent marketplace (Sprint 7) | R3 | 15 | 20 | bar: 2027-02-01 to 2027-03-08
D10 | Multi-model routing | R3 | 14 | 17 | bar: 2027-01-25 to 2027-02-15
D11 | Prompt registry + eval regression suite | R3 | 16 | 19 | bar: 2027-02-08 to 2027-03-01
Memory
E1 | Cosmos DB + memory schema | R2 | 8 | 10 | bar: 2026-12-14 to 2026-12-28
E2 | Session & project memory API | R2 | 10 | 13 | bar: 2026-12-28 to 2027-01-18
E3 | Correction Store indexed to AI Search | R2 | 11 | 14 | bar: 2027-01-04 to 2027-01-25
E4 | Approved-pattern library | R3 | 15 | 18 | bar: 2027-02-01 to 2027-02-22
E5 | Memory governance | R3 | 17 | 19 | bar: 2027-02-15 to 2027-03-01
Editor
F1 | Editor endpoint config + Entra sign-in | MVP | 5 | 8 | bar: 2026-11-23 to 2026-12-14
F3 | Pipeline UX for Azure status/errors | MVP | 7 | 8 | bar: 2026-12-07 to 2026-12-14
F4 | Installer + update channel | R2 | 11 | 14 | bar: 2027-01-04 to 2027-01-25
F5 | Telemetry (opt-in) + usage dashboard | R3 | 16 | 18 | bar: 2027-02-08 to 2027-02-22
Continuum Integration
G1 | Continuum service-token API + OpenAPI spec | MVP | 3 | 6 | bar: 2026-11-09 to 2026-11-30
G2 | DarkHorse ContinuumClient (pull specs) | MVP | 5 | 8 | bar: 2026-11-23 to 2026-12-14
G3 | Push-back from DarkHorse | R2 | 9 | 12 | bar: 2026-12-21 to 2027-01-11
G4 | Approval webhook -> DarkHorse run | R2 | 11 | 14 | bar: 2027-01-04 to 2027-01-25
G5 | Continuum schema additions | R2 | 9 | 11 | bar: 2026-12-21 to 2027-01-04
G6 | Continuum on Azure + Entra SSO | R2 | 7 | 11 | bar: 2026-12-07 to 2027-01-04
G7 | Continuum AI via LLM proxy | R2 | 10 | 12 | bar: 2026-12-28 to 2027-01-11
G8 | Continuum UI: Generate with DarkHorse | R3 | 14 | 18 | bar: 2027-01-25 to 2027-02-22
ChickletFlow Integration
H1 | ChickletFlow auth (Entra + service tokens) | R2 | 6 | 9 | bar: 2026-11-30 to 2026-12-21
H2 | Work item link fields | R2 | 8 | 10 | bar: 2026-12-14 to 2026-12-28
H3 | Events endpoint + status_history source | R2 | 9 | 12 | bar: 2026-12-21 to 2027-01-11
H4 | DarkHorse StatusReporter | R2 | 11 | 14 | bar: 2027-01-04 to 2027-01-25
H5 | Auto-status mapping rules | R2 | 12 | 14 | bar: 2027-01-11 to 2027-01-25
H6 | ChickletFlow on Azure | R2 | 8 | 11 | bar: 2026-12-14 to 2027-01-04
H7 | Board: run badge + delivery dashboard | R3 | 15 | 19 | bar: 2027-02-01 to 2027-03-01
Cross-Product
I1 | Unified identity (Entra groups/roles) | MVP | 5 | 8 | bar: 2026-11-23 to 2026-12-14
I2 | Event and ID contract | R0 | 2 | 4 | bar: 2026-11-02 to 2026-11-16
I3 | End-to-end UAT | R3 | 18 | 20 | bar: 2027-02-22 to 2027-03-08
I4 | Internal pilot on one RICEFW | MVP | 7 | 8 | bar: 2026-12-07 to 2026-12-14
I5 | Wider program pilot | GA | 21 | 23 | bar: 2027-03-15 to 2027-03-29
Release & Governance
J1 | Threat model + security design review | R0 | 2 | 3 | bar: 2026-11-02 to 2026-11-09
J2 | Documentation + training | GA | 18 | 23 | bar: 2027-02-22 to 2027-03-29
J3 | GA readiness + go-live | GA | 23 | 24 | bar: 2027-03-29 to 2027-04-05
J4 | Security review + penetration test | GA | 21 | 23 | bar: 2027-03-15 to 2027-03-29

## Release Plan
Release plan - when each feature goes live
Release weeks are the source of truth; each Planned feature must finish by its release week.
Release | Name | Week | Go-live date (Fri) | Environment | New features | Go/no-go criteria
R0 | R0 - Azure Foundations (dev env live) | 4 | 2026-11-20 | Azure dev | 7 | IaC reproducible; CI/CD green; MCP + LLM proxy reachable in dev; KB in index v2; contract drafted
MVP | MVP - DarkHorse on Azure, Continuum read integration, internal pilot | 8 | 2026-12-18 | Azure prod (internal pilot) | 16 | Entra auth enforced; retrieval eval above agreed threshold; one real RICEFW end to end; rollback tested; budgets/alerts live
R2 | R2 - Memory, Clean Core loop, full Continuum + ChickletFlow integration | 14 | 2027-01-29 | Azure prod (pilot teams) | 24 | Clean Core loop pass-rate target met; Continuum webhook -> run -> push-back -> ChickletFlow status works; auth on all three apps
R3 | R3 - Marketplace, multi-model, private networking, dashboards | 20 | 2027-03-12 | Azure prod (all programs) | 11 | UAT across 5+ RICEFW types; private networking validated; marketplace install/update works
GA | GA - Production hardening, client-tenant template, security sign-off | 24 | 2027-04-09 | Azure prod + client-tenant template | 6 | Pen-test findings closed; DR test passed; docs + training done; support model and SLA agreed
Features by release
Release | Feature | ID | Go-live date | Workstream | MVP? | Priority
Shipped | Ingest framework + 8 fetchers + Azure embedder/index | B0 | Live (v0.7.38) | RAG & Knowledge |  | High
Shipped | MCP tools (verify_badi/exit, clean core level, CDS, EML, RAP, CBO) | C1 | Live (v0.7.38) | MCP Server |  | High
Shipped | Grounded Code/TDS/SO/FDS agents | D1 | Live (v0.7.38) | Agents & Pipeline |  | High
Shipped | ReviewAgent + auto-rewrite + ZI_ wrappers | D2 | Live (v0.7.38) | Agents & Pipeline |  | High
Shipped | TdsPostCodeAgent | D3 | Live (v0.7.38) | Agents & Pipeline |  | Med
Shipped | Solution architecture diagram | D4 | Live (v0.7.38) | Agents & Pipeline |  | Med
Shipped | Extension v0.7.38 + version in status bar | F2 | Live (v0.7.38) | Editor |  | Low
R0 | Azure landing zone + IaC | A1 | 2026-11-20 | Azure Platform | Yes | High
R0 | Azure OpenAI / Foundry deployments | A2 | 2026-11-20 | Azure Platform | Yes | High
R0 | Azure AI Search + index schema v2 | A3 | 2026-11-20 | Azure Platform | Yes | High
R0 | Containerize services | A4 | 2026-11-20 | Azure Platform | Yes | High
R0 | CI/CD pipelines | A7 | 2026-11-20 | Azure Platform | Yes | High
R0 | Event and ID contract | I2 | 2026-11-20 | Cross-Product | Yes | High
R0 | Threat model + security design review | J1 | 2026-11-20 | Release & Governance | Yes | High
MVP | Container Apps env + APIM + Front Door | A5 | 2026-12-18 | Azure Platform | Yes | High
MVP | Entra ID auth + managed identity | A6 | 2026-12-18 | Azure Platform | Yes | High
MVP | Observability + cost controls | A8 | 2026-12-18 | Azure Platform | Yes | Med
MVP | Prod environment + go-live runbook | A9 | 2026-12-18 | Azure Platform | Yes | High
MVP | Scheduled ingest job on Azure | B1 | 2026-12-18 | RAG & Knowledge | Yes | High
MVP | Re-ingest KB with hybrid + metadata filters | B2 | 2026-12-18 | RAG & Knowledge | Yes | High
MVP | Retrieval quality eval harness | B8 | 2026-12-18 | RAG & Knowledge | Yes | High
MVP | MCP HTTP/SSE transport + auth middleware | C2 | 2026-12-18 | MCP Server | Yes | High
MVP | MCP uses managed identity for Search | C3 | 2026-12-18 | MCP Server | Yes | High
MVP | LLM proxy on Azure | D6 | 2026-12-18 | Agents & Pipeline | Yes | High
MVP | Editor endpoint config + Entra sign-in | F1 | 2026-12-18 | Editor | Yes | High
MVP | Pipeline UX for Azure status/errors | F3 | 2026-12-18 | Editor | Yes | Med
MVP | Continuum service-token API + OpenAPI spec | G1 | 2026-12-18 | Continuum Integration | Yes | High
MVP | DarkHorse ContinuumClient (pull specs) | G2 | 2026-12-18 | Continuum Integration | Yes | High
MVP | Unified identity (Entra groups/roles) | I1 | 2026-12-18 | Cross-Product | Yes | High
MVP | Internal pilot on one RICEFW | I4 | 2026-12-18 | Cross-Product | Yes | High
R2 | EDMX live run (XSUAA auth) | B3 | 2027-01-29 | RAG & Knowledge |  | High
R2 | help-portal-cds re-crawl | B4 | 2027-01-29 | RAG & Knowledge |  | Med
R2 | KB coverage gap closure | B5 | 2027-01-29 | RAG & Knowledge |  | High
R2 | Blob raw cache + ingest versioning | B7 | 2027-01-29 | RAG & Knowledge |  | Med
R2 | New MCP tools | C4 | 2027-01-29 | MCP Server |  | High
R2 | MCP rate limits, audit logs, tenant filters | C5 | 2027-01-29 | MCP Server |  | Med
R2 | Headless agent service on Azure | D5 | 2027-01-29 | Agents & Pipeline |  | High
R2 | Clean Core validation loop | D7 | 2027-01-29 | Agents & Pipeline |  | High
R2 | Source citations in generated output | D8 | 2027-01-29 | Agents & Pipeline |  | Med
R2 | Cosmos DB + memory schema | E1 | 2027-01-29 | Memory |  | High
R2 | Session & project memory API | E2 | 2027-01-29 | Memory |  | High
R2 | Correction Store indexed to AI Search | E3 | 2027-01-29 | Memory |  | High
R2 | Installer + update channel | F4 | 2027-01-29 | Editor |  | Med
R2 | Push-back from DarkHorse | G3 | 2027-01-29 | Continuum Integration |  | High
R2 | Approval webhook -> DarkHorse run | G4 | 2027-01-29 | Continuum Integration |  | High
R2 | Continuum schema additions | G5 | 2027-01-29 | Continuum Integration |  | High
R2 | Continuum on Azure + Entra SSO | G6 | 2027-01-29 | Continuum Integration |  | High
R2 | Continuum AI via LLM proxy | G7 | 2027-01-29 | Continuum Integration |  | Med
R2 | ChickletFlow auth (Entra + service tokens) | H1 | 2027-01-29 | ChickletFlow Integration |  | High
R2 | Work item link fields | H2 | 2027-01-29 | ChickletFlow Integration |  | High
R2 | Events endpoint + status_history source | H3 | 2027-01-29 | ChickletFlow Integration |  | High
R2 | DarkHorse StatusReporter | H4 | 2027-01-29 | ChickletFlow Integration |  | High
R2 | Auto-status mapping rules | H5 | 2027-01-29 | ChickletFlow Integration |  | Med
R2 | ChickletFlow on Azure | H6 | 2027-01-29 | ChickletFlow Integration |  | High
R3 | Private networking | A10 | 2027-03-12 | Azure Platform |  | Med
R3 | LearningPortalFetcher | B6 | 2027-03-12 | RAG & Knowledge |  | Low
R3 | Agent marketplace (Sprint 7) | D9 | 2027-03-12 | Agents & Pipeline |  | Med
R3 | Multi-model routing | D10 | 2027-03-12 | Agents & Pipeline |  | Med
R3 | Prompt registry + eval regression suite | D11 | 2027-03-12 | Agents & Pipeline |  | Med
R3 | Approved-pattern library | E4 | 2027-03-12 | Memory |  | Med
R3 | Memory governance | E5 | 2027-03-12 | Memory |  | Med
R3 | Telemetry (opt-in) + usage dashboard | F5 | 2027-03-12 | Editor |  | Low
R3 | Continuum UI: Generate with DarkHorse | G8 | 2027-03-12 | Continuum Integration |  | Med
R3 | Board: run badge + delivery dashboard | H7 | 2027-03-12 | ChickletFlow Integration |  | Med
R3 | End-to-end UAT | I3 | 2027-03-12 | Cross-Product |  | High
GA | Per-client deployment template | A11 | 2027-04-09 | Azure Platform |  | High
GA | DR, backup, load and pen-test remediation | A12 | 2027-04-09 | Azure Platform |  | High
GA | Wider program pilot | I5 | 2027-04-09 | Cross-Product |  | High
GA | Documentation + training | J2 | 2027-04-09 | Release & Governance |  | Med
GA | GA readiness + go-live | J3 | 2027-04-09 | Release & Governance |  | High
GA | Security review + penetration test | J4 | 2027-04-09 | Release & Governance |  | High
Formulas:
Go-live date (Fri) = Summary!$C4+7*([Week]-1)+4

## Integration
System | Area | Type | Change required | Where (code) | Release | Start wk | End wk | Start date | End date | Person-weeks | Owner
Continuum | Auth | API | Add service-token (API key / Entra client-credential) auth alongside NextAuth sessions so DarkHorse can call ricefw endpoints | lib/auth.ts, middleware.ts, app/api/w/[slug]/ricefws/* | MVP | 3 | 6 | 2026-11-09 | 2026-12-04 | 3 | TBD
Continuum | API contract | API | Publish OpenAPI spec for read of latest APPROVED RicefwVersion sections (BR, FD, TD, Test, Cutover) by workspace slug + objectId | app/api/w/[slug]/ricefws/[id]/route.ts | MVP | 3 | 6 | 2026-11-09 | 2026-12-04 | 1 | TBD
Continuum | Schema | Data model | Add darkhorseRunId, cleanCoreScore, generatedObjects (JSON) to Ricefw/RicefwVersion; add DARKHORSE to TraceSystem enum; Prisma migration | prisma/schema.prisma (Ricefw, TraceLink, TraceSystem) | R2 | 9 | 11 | 2026-12-21 | 2027-01-08 | 2 | TBD
Continuum | Write-back | API | Endpoint to create DRAFT version from DarkHorse and attach generated TDS/code/diagram/Clean Core report as Attachments | app/api/w/[slug]/ricefws/[id]/attachments, versions | R2 | 9 | 12 | 2026-12-21 | 2027-01-15 | 3 | TBD
Continuum | Webhook | API | Emit signed webhook on approval (APPROVED/PUBLISHED) to DarkHorse agent service; retry + dead-letter | app/api/w/[slug]/ricefws/[id]/approvals/route.ts, status/route.ts | R2 | 11 | 14 | 2027-01-04 | 2027-01-29 | 3 | TBD
Continuum | Identity | Auth | Replace credentials/invite-only auth with Entra ID SSO; map Entra groups to WorkspaceRole | app/api/auth/[...nextauth], lib/auth.ts | R2 | 7 | 11 | 2026-12-07 | 2027-01-08 | 3 | TBD
Continuum | AI | Code | Route lib/ai (enhanceField) through the Azure LLM proxy instead of direct ANTHROPIC_API_KEY | lib/ai.ts, app/api/w/[slug]/ai/enhance/route.ts | R2 | 10 | 12 | 2026-12-28 | 2027-01-15 | 2 | TBD
Continuum | Deploy | Infra | Container Apps + Azure Postgres Flexible Server; Key Vault for AUTH_SECRET; run prisma migrate deploy in release pipeline | Dockerfile, docker-compose.yml | R2 | 7 | 11 | 2026-12-07 | 2027-01-08 | 4 | TBD
Continuum | UI | UI | Generate with DarkHorse button, run status panel, Clean Core score badge on RICEFW page | components/*, app/w/[slug]/... | R3 | 14 | 18 | 2027-01-25 | 2027-02-26 | 4 | TBD
ChickletFlow | Auth | Auth | Add Entra ID auth + service tokens to FastAPI and /ws/board (currently open; CORS only) | backend/app/main.py, config.py, websocket.py | R2 | 6 | 9 | 2026-11-30 | 2026-12-25 | 3 | TBD
ChickletFlow | Schema | Data model | Add continuum_object_id, continuum_url, darkhorse_run_id, clean_core_score to work_items; Alembic migration | backend/app/models.py, schemas.py, alembic/ | R2 | 8 | 10 | 2026-12-14 | 2027-01-01 | 2 | TBD
ChickletFlow | Events | API | POST /api/work-items/{id}/events for DarkHorse/Continuum; add source column to status_history; broadcast over WebSocket | backend/app/routers/work_items.py, crud.py, websocket.py | R2 | 9 | 12 | 2026-12-21 | 2027-01-15 | 3 | TBD
ChickletFlow | Status mapping | Code | Configurable mapping: Continuum approval and DarkHorse stages -> board columns (Build In-Progress, TS Updates/TUT/Code Review, Blocked on failure) | backend/app/crud.py, routers/status_duration.py | R2 | 12 | 14 | 2027-01-11 | 2027-01-29 | 2 | TBD
ChickletFlow | Import | Code | Excel import maps story ID to Continuum objectId automatically | backend/app/excel_import.py | R2 | 10 | 11 | 2026-12-28 | 2027-01-08 | 1 | TBD
ChickletFlow | Deploy | Infra | Container Apps + Azure Postgres Flexible; WebSocket support (ingress or Azure Web PubSub); Alembic on deploy | docker-compose.yml, backend/ | R2 | 8 | 11 | 2026-12-14 | 2027-01-08 | 3 | TBD
ChickletFlow | UI | UI | DarkHorse run badge, Clean Core score on chicklet; cycle-time and throughput dashboard | frontend/src/* | R3 | 15 | 19 | 2027-02-01 | 2027-03-05 | 4 | TBD
DarkHorse | Client | Code | ContinuumClient: pull approved specs by objectId as pipeline input (replaces manual docx) | extensions/darkhorse-pipeline/src | MVP | 5 | 8 | 2026-11-23 | 2026-12-18 | 3 | TBD
DarkHorse | Client | Code | Push-back of generated artifacts to Continuum; StatusReporter to ChickletFlow | extensions/darkhorse-pipeline/src, new agent service | R2 | 9 | 14 | 2026-12-21 | 2027-01-29 | 4 | TBD
DarkHorse | Service | Code | Headless agent service exposing run API (start, status, cancel) for Continuum webhook | extensions/darkhorse-agents -> services/ | R2 | 9 | 14 | 2026-12-21 | 2027-01-29 | 6 | TBD
All | Contract | Design | Shared event/ID contract and versioning (RICEFW ID, run id, status events) | docs/ (new integration spec) | R0 | 2 | 4 | 2026-11-02 | 2026-11-20 | 2 | TBD
Formulas:
Start date = Summary!$C4+7*([Start wk]-1)
End date = Summary!$C4+7*([End wk]-1)+4

## Azure Deployment
Step | Phase | What gets deployed | Features | Start wk | End wk | Start date | End date | Environment
1 | Foundation | Subscription, RBAC, naming/tagging, resource groups dev/prod, Key Vault, ACR, Log Analytics | A1, J1 | 1 | 3 | 2026-10-26 | 2026-11-13 | Dev
2 | AI services | Azure OpenAI chat + embeddings deployments, AI Search S1 + semantic ranker | A2, A3 | 1 | 4 | 2026-10-26 | 2026-11-20 | Dev
3 | Containers + CI/CD | Dockerfiles, ACR push, Container Apps env, GitHub Actions | A4, A7 | 3 | 4 | 2026-11-09 | 2026-11-20 | Dev
4 | Dev live (R0) | MCP + LLM proxy reachable in dev; KB ingested to index v2 | M1 | 4 | 4 | 2026-11-16 | 2026-11-20 | Dev
5 | Edge + identity | APIM, Front Door, Entra app registration, managed identities | A5, A6 | 4 | 7 | 2026-11-16 | 2026-12-11 | Dev -> Prod
6 | Ingest + retrieval | Scheduled ingest job, hybrid index, eval harness | B1, B2, B8 | 5 | 8 | 2026-11-23 | 2026-12-18 | Dev -> Prod
7 | Observability | App Insights, dashboards, alerts, budgets | A8 | 6 | 8 | 2026-11-30 | 2026-12-18 | Dev -> Prod
8 | Prod + MVP go-live | Prod env, runbook, smoke tests, pilot RICEFW | A9, I4 | 7 | 8 | 2026-12-07 | 2026-12-18 | Prod
9 | Continuum + ChickletFlow to Azure | Container Apps + Postgres Flexible for both apps; Entra SSO | G6, H6, H1 | 6 | 11 | 2026-11-30 | 2027-01-08 | Dev -> Prod
10 | Memory + agent service | Cosmos DB, headless agent service, MCP memory tools | E1, D5 | 8 | 14 | 2026-12-14 | 2027-01-29 | Prod
11 | Private networking | VNet, Private Endpoints, optional no-public-access | A10 | 16 | 20 | 2027-02-08 | 2027-03-12 | Prod
12 | Client-tenant template + DR | Parameterized IaC for client subscriptions, DR test, pen-test fixes | A11, A12 | 20 | 24 | 2027-03-08 | 2027-04-09 | Prod / Client
Key Azure dates
| Dev environment live | Week 4 |  |  |  | 2026-11-20
| Prod environment + MVP go-live | Week 8 |  |  |  | 2026-12-18
| Continuum + ChickletFlow on Azure | Week 11 |  |  |  | 2027-01-08
| Integrated release (R2) | Week 14 |  |  |  | 2027-01-29
| Private networking done | Week 20 |  |  |  | 2027-03-12
| GA / client-tenant template | Week 24 |  |  |  | 2027-04-09
Formulas:
Start date = Summary!$C4+7*([Start wk]-1)
End date = Summary!$C4+7*([End wk]-1)+4

## Effort by Workstream
Workstream | R0 | MVP | R2 | R3 | GA | Total (pw)
Azure Platform | 10 | 10 | 0 | 4 | 7 | 31
RAG & Knowledge | 0 | 7 | 10 | 1 | 0 | 18
MCP Server | 0 | 3 | 5 | 0 | 0 | 8
Agents & Pipeline | 0 | 3 | 12 | 12 | 0 | 27
Memory | 0 | 0 | 8 | 5 | 0 | 13
Editor | 0 | 4 | 2 | 2 | 0 | 8
Continuum Integration | 0 | 6 | 14 | 4 | 0 | 24
ChickletFlow Integration | 0 | 0 | 16 | 4 | 0 | 20
Cross-Product | 2 | 3 | 0 | 3 | 3 | 11
Release & Governance | 1 | 0 | 0 | 0 | 8 | 9
Total | 13 | 36 | 67 | 35 | 18 | 169
Person-weeks are first-pass estimates. Divide by team size and release duration to check capacity.

## Risks & Questions
Risk | Impact | Mitigation | Related
Azure OpenAI quota/model availability delays | High | Request quota in week 1; keep adapter ready for Claude on Foundry / alternate region | A2
Holiday weeks (W9-W10, Dec 21 - Jan 1) reduce capacity | Med | MVP go-live set in W8; W9-10 are hypercare/buffer only | M4, M5
EDMX download requires XSUAA auth | Med | BTP trial or bearer token path; fall back to catalog-only metadata | B3
ChickletFlow has no auth today; exposing it on Azure is risky | High | Entra + service tokens (H1) must land before any public ingress | H1
Three-team contract drift (IDs, statuses) | High | Contract sign-off at M2; versioned events; contract tests in CI | I2
Retrieval quality limits Clean Core accuracy | High | Eval harness (B8) gates KB changes; coverage gap closure (B5) | B5, B8
Client data residency / tenant isolation | High | Per-client index filter, per-client deployment template, private networking | A10, A11, E5
Cost growth from AI Search + OpenAI usage | Med | Budgets and token metering from MVP (A8, D6) | A8
Team capacity unknown (owners are TBD) | High | Assign owners in Features sheet; use Person-Weeks column to check load by workstream | All
Open decisions
1. Central multi-tenant Deloitte instance vs per-client deployment? (drives A11, E5)
2. Which chat model is approved/quota-available in your Azure region?
3. Does darkhorse-mcp already serve HTTP or only stdio? (confirm before C2)
4. Who owns each workstream (owners are TBD)?
5. Should Continuum remain invite-only for external client users, or federate client identities (Entra B2B)?
6. Which Continuum approval state should trigger DarkHorse (APPROVED vs PUBLISHED)?